## Risks
CoSpace - Risk List
Risk ID | Date Identified | Headline | Description | Type | Impact | Probability | Magnitude | Owner | Mitigation Strategy
1 | 2021-04-18 | Incorrect Understanding of the Requirements | One or more of the requirements of the software are wrongly understood. Potential impacts of this risk include: Time and cost are wasted, the failure of meeting the requirements of the project results in a failure to meet the needs of the stakeholders. | D | 10 | 2 | 20 | Software Analyst | Establish effective communication links between stakeholders and customers to avoid the risk. Ensure both sides understood the same objective. Request feedback on the our understanding, frequently. Develop the software in a modular way using information hiding techniques.
2 | 2021-03-26 | Team Member Not Available Due to Health Reasons | One or more members of the development team are sick. Potential impacts of this risk include: Development task assigned to said team member are not completed, and the transfer of the said task results in a disruption in development activities. | I | 5 | 5 | 25 | Project Manager | Rearrange the tasks and team to minimize the impact of the absence of the team member.
3 | 2021-05-01 | Team Member Has Left the Team | One or more members of the development team has left the group before the completion of the project. Potential impacts of this risk include: Development task assigned to said team member are not completed, and the transfer of the said tasks results in a disruption in development activities. As the human resource required to complete the project in time reduced, potential delays may occur. | I | 8 | 1 | 8 | Project Manager | Rearrange the tasks and team to minimize the impact of the absence of the team member. Inform the stakeholders about the situation.
4 | 2021-05-01 | Technical Skills Required for the Development Task Is Underestimated | The technical skills required for completion of a development task is underestimated. | D | 3 | 5 | 15 | Development Team Members | Increase the collaboration and information sharing between team members. Use techniques like extreme programming and pair programming.
5 | 2021-05-01 | Time Required for Completion of The Development Is Underestimated | The time required for the completion of the software is underestimated. Potential impacts of this risk include: Delays in the delivery of the software and bad customer experience. | D | 9 | 2 | 18 | Project Manager | Inform the stakeholders about the situation, increase efforts to develop the project, and demand extensions to deadlines if necessary.
6 | 2021-05-01 | Requirements Changed | One or more requirements of the project are changed after they’ve been implemented. Potential impacts of this risk include: Potential delays in the delivery of the software. If the requirement change is great, restructuring of the architecture may be needed. | I | 10 | 2 | 20 | Software Analyst | Inform the stakeholders about the potential delays and the impact of the changed requirement. Develop the software in a modular way using information hiding techniques, so that the system is tolerant to changes.
7 | 2021-05-01 | Software Defect is Discovered | A serious software defect is discovered shortly before the delivery of the software. Potential impacts of this risk include: Potential delays in the delivery of the software. | D | 8 | 3 | 24 | Software Tester | Conduct effective unit tests and integration tests to reduce the possibility of unseen defects in the software. If it is too late, inform the stakeholders about the situation.
8 | 2021-05-01 | Task Wrongly Understood | A development task assigned to a member of the development team is wrongly understood by the team member. Potential impacts of this risk include: Potential delays in the completion of the development task, time and budget wasted. | D | 3 | 6 | 18 | Software Analyst, Project Manager | Ensure strong and effective communication between the team members.
9 | 2021-05-01 | Task is Taking Much Time | A development task is taking too much time to complete. Potential impacts of this risk include: Potential delays in the estimated completion time of the development task, time and budget wasted. | D | 2 | 6 | 12 | Development Team Members | Use techniques such as extreme programming and pair programming to reduce the time required to complete the task. Reassign work items to other team members f necessary.
10 | 2021-05-01 | Task is Blocked | A development task is blocking another development task to be completed. Potential impacts of this risk include: Potential delays in the estimated completion time of the blocked development task. Time and budget wasted. | D | 6 | 4 | 24 | Project Manager, Development Team Members | Inform the team member responsible for the task and use programming techniques such as pair programming to reduce the impact of the situation